## input I
Качественная оценка переменных
Input Variables Description
long name | short name | very low / bad / unsatisfactory | low / unsatisfactory | moderate | high / satisfactory | very high / good / satisfactory
• Basic design data | data | v. low | low | moderate | high | v. high
• 3D CAD modeling | cad | limited use | limited/normal | normal use | normal/extensive | extensive use
• Change communication system | comm | low | low-moderate | moderate | moderate-high | high
• Constructor input | constr | v. low | low | moderate | high | v. high
• Design-construction overlap | overlap | 90% - "fast track" | 70% - "fast track / normal" | 50% - "normal" | 30% - "non schedule driven / normal" | 10% - "non-schedule driven"
• Designer previous experience w/ process technology | designer | 100% new | 75% new | 50% new | 25% new | duplicate or scale
• Designer qualifications and capacity | qualifi | v. low | low | moderate | high | v. high
• Owner previous experience w/ process technology | owner | 100% new | 75% new | 50% new | 25% new | duplicate or scale
• Percent TIC scope changes | percent | 9% | 7% | 5% | 3% | 1%
• Project size | size | About $90M | About $70M | About $50M | About $30M | About $10M
• Relative size of project (compared to other projects from the same industry sector) | resize | v. large | large | medium | small | v. small
• Scope completeness / Scope Definition | scope | v. low | low | moderate | high | v. high
• Site conditions | site | significant impact | slightly more than normal impact | typical Impact | little Impact (new unit in existing plant) | insignificant impact
• Split engineering practices | split | Yes | Yes | Yes/No | No | No
• Use of integrated databases | id | limited use | limited/normal | normal use | normal/extensive | extensive use
Принимаемые значенгия переменных в зависимости от качественной оценки
Input Variables values
long name | short name | very low / bad / unsatisfactory | low / unsatisfactory | moderate | high / satisfactory | very high / good / satisfactory
• Basic design data | data | 1 | 3 | 5 | 7 | 9
• 3D CAD modeling | cad | 1 | 2 | 3 | 4 | 5
• Change communication system | comm | 1 | 2 | 3 | 4 | 5
• Constructor input | constr | 1 | 3 | 5 | 7 | 9
• Design-construction overlap | overlap | 9 | 7 | 5 | 3 | 1
• Designer previous experience w/ process technology | designer | 5 | 4 | 3 | 2 | 1
• Designer qualifications and capacity | qualifi | 1 | 3 | 5 | 7 | 9
• Owner previous experience w/ process technology | owner | 5 | 4 | 3 | 2 | 1
• Percent TIC scope changes | percent | 9 | 7 | 7 | 3 | 1
• Project size | size | 9 | 7 | 5 | 3 | 1
• Relative size of project (compared to other projects from the same industry sector) | resize | 5 | 4 | 3 | 2 | 1
• Scope completeness / Scope Definition | scope | 1 | 3 | 5 | 7 | 9
• Site conditions | site | 5 | 4 | 3 | 2 | 1
• Split engineering practices | split | 3 | 3 | 2 | 1 | 1
• Use of integrated databases | id | 1 | 2 | 3 | 4 | 5

## input II
Basic Design Data
• General plant identification
• General project summary
• Process description
• Special requirements of design, startup, shut downs, site, and material handling
• Environmental data
• Cost considerations
• General service and yard facilities
• PFD
• P&IDs and supporting data
Scope completeness / Scope Definition
• Project type and facility description
• Data availability
• Objectives and priorities incl. cost, schedule, capacity and quality
• Description of new process equipment
• Vendor data
• Reference on process fluids, materials of construction and type of instrumentation.
• Automated system requirements
• Special alternates needed
Designer qualifications and capacity
• Designer organization
• Experience with similar projects
• Knowledge of the technology
• Management of changes
• Project team qualifications
• Project team continuity
• Contract agreement
• Design approach
• Capacity, readiness and computer capabilities
Construction Input
• Labor and material availability
• Appropriate construction methods and technology
• Construction sequence
• New concepts or materials or systems
• Practical advice on field conditions, safety and labor conditions
• Design approach Constructability team activity during detailed design

## engineering efficiency PLAN
при нимаемые значения → |  |  | от 1 до 9 | от 1 до 5 | от 1 до 5 | от 1 до 9 | от 9 до 1 | от 5 до 1 | от 1 до 9 | от 5 до 1 | от 9 до 1 | от 9 до 1 | от 5 до 1 | от 1 до 9 | от 5 до 1 | от 3 до 1 | от 1 до 5
factors long name /факторы длинное имя → |  |  | • Basic design data | • 3D CAD modeling | • Change communication system | • Constructor input | • Design-construction overlap | • Designer previous experience w/ process technology | • Designer qualifications and capacity | • Owner previous experience w/ process technology | • Percent TIC scope changes | • Project size | • Relative size of project | • Scope completeness / Scope Definition | • Site conditions | • Split engineering practices | • Use of integrated databases | Factor Function |  |  |  | Productivity function
factors short name / факторы короткое имя → | worst | best | data | cad | comm | constr | overlap | designer | qualifi | owner | percent | size | resize | scope | site | split | id | doun border when function is "0" | upper border when function is "1" | assumed for calculation | Factor value (assessment function) | coefficient | value by the chapter
factors assumed value / значение, принятое в расчете → |  |  | 7 | 4 | 4 | 5 | 4 | 4 | 7 | 3 | 4 | 3 | 2 | 6 | 3 | 3 | 3
%Engineering rework / %Перепроектирование | 9.2% | 2.2% |  | -0.0064457 | -0.046409 | -0.010716 | [11 empty] | 9.2% | 2.2% | 4.379% | 0.68429 | 0.069 | 0.047216
Design document release commitment / Обязательство по выпуску проектной документации | 1 | 5 | [9 empty] | -0.18634 | -0.6087 | 1.1553 |  | -1.118 |  | 2 | 4 | 3.2484 | 0.62422 | 0.117 | 0.073034
%Detailed design schedule delay / %Задержка в графике детального проектирования | 16% | 5.2% | [9 empty] | 0.016531 |  |  | 0.047939 |  |  | 16% | 5.2% | 9.498% | 0.60049 | 0.099 | 0.059448
%Detailed design cost overrun / %Превышение затрат на детальное проектирование | 19% | 6% | [6 empty] | -0.085558 | 0.024164 | [7 empty] | 19% | 6% | 10.06% | 0.68673 | 0.033 | 0.022662
%Fabrication & construction schedule delay due to design deficiencies / %Задержка в сроках изготовления и строительства из-за недостатков проекта | 8% | 2.8% |  |  |  | -0.012871 |  | 0.018535 | [6 empty] | 0.0096535 |  |  | 8% | 2.8% | 5.863% | 0.41247 | 0.196 | 0.080845
%Fabrication & construction cost increase due to design deficiencies / %Увеличение стоимости изготовления и строительства из-за недостатков проекта | 5.8% | 1.8% |  |  |  | -0.016667 | [10 empty] | -0.01 | 5.8% | 1.8% | 3.8% | 0.5 | 0.11 | 0.055
%Construction hours for design problem solving / %Строительные часы, затрачиваемые на решение проектных задач | 5 | 1 |  |  |  | -0.2907 | 1.7674 | [10 empty] | 3 | 2 | 2.5581 | 0.44186 | 0.062 | 0.027395
%Estimated constructability Dollar savings / %Экономия средств на строительстве | 1 | 5 | 0.99432 |  |  | 1.0298 |  |  |  |  | -0.30114 | -0.23011 | [5 empty] | 2 | 4 | 3.5128 | 0.75639 | 0.115 | 0.086985
%Start-up schedule delay due to design deficiencies / %Задержка ввода в эксплуатацию из-за недостатков проекта | 8.4% | 3.6% | [5 empty] | 0.010605 |  | 0.015112 |  |  |  | -0.0076355 | 0.0052988 |  |  | 8.4% | 3.6% | 6.138% | 0.47148 | 0.139 | 0.065536
%Start-up cost increase due to design deficiencies / % Рост стоимости ввода в эксплуатацию из-за недостатков проекта | 6.4% | 2.2% | [5 empty] | 0.042001 | [9 empty] | 6.4% | 2.2% | 5.35% | 0.24617 | 0.06 | 0.01477
0.53289

## engineering efficiency FACT
|  | levels of factors |  |  |  |  | Factor Function |  |  |  | Productivity function
Engineering Performance Measures | Factor Designation | veri low / very unsatisfactory | low / unsatisfactory | moderate | high / satisfactory | veri high / very satisfactory | doun border when function is "0" | upper border when function is "1" | assumed for calculation | Factor value (assessment function) | coefficient | value by the chapter
%Engineering rework / %Перепроектирование | y1 | 9.2% | 7.8% | 6.8% | 4.6% | 2.2% | 9.2% | 2.2% | 3% | 0.8813 | 0.069 | 0.06081
Design document release commitment / Обязательство по выпуску проектной документации | y2 | 1=very unsatisfactory | 2=unsatisfactory | 3=moderate | 4=satisfactory | 5=very satisfactory | 2 | 4 | 3 | 0.5 | 0.117 | 0.0585
%Detailed design schedule delay / %Задержка в графике детального проектирования | y3 | 16% |  |  |  | 5.2% | 16% | 5.2% | 6% | 0.9244 | 0.099 | 0.091516
%Detailed design cost overrun / %Превышение затрат на детальное проектирование | y4 | 19% |  |  |  | 6% | 19% | 6% | 9% | 0.7679 | 0.033 | 0.025341
%Fabrication & construction schedule delay due to design deficiencies / %Задержка в сроках изготовления и строительства из-за недостатков проекта | y5 | 8% |  |  |  | 2.8% | 8% | 2.8% | 3% | 0.9631 | 0.196 | 0.18877
%Fabrication & construction cost increase due to design deficiencies / %Увеличение стоимости изготовления и строительства из-за недостатков проекта | y6 | 5.8% |  |  |  | 1.8% | 5.8% | 1.8% | 2% | 0.95 | 0.11 | 0.1045
%Construction hours for design problem solving / %Строительные часы, затрачиваемые на решение проектных задач | y7 | 5=very high | 4=high | 3=moderate | 2=low | 1=very low | 3 | 2 | 2 | 1 | 0.062 | 0.062
%Estimated constructability Dollar savings / %Экономия средств на строительстве | y8 | 1=very low | 2=low | 3=moderate | 4=high | 5=very high | 2 | 4 | 4 | 1 | 0.115 | 0.115
%Start-up schedule delay due to design deficiencies / %Задержка ввода в эксплуатацию из-за недостатков проекта | y9 | 8.4% |  |  |  | 3.6% | 8.4% | 3.6% | 4% | 0.9168 | 0.139 | 0.12744
%Start-up cost increase due to design deficiencies / % Рост стоимости ввода в эксплуатацию из-за недостатков проекта | y10 | 6.4% |  |  |  | 2.2% | 6.4% | 2.2% | 3% | 0.8057 | 0.06 | 0.048342
TOTAL Effective Productivity FACT assessment | [11 empty] | 0.88221